## Construction Gantt Chart
IT CAPSTONE
Project: |  | Mixology Website
Team Members : |  | George, Paul, Anthony
Website Gantt Chart
Mixology Website |  |  | DURATION (Days)
START DATE | END DATE | DESCRIPTION
2020-09-02 | 2020-09-03 | Kick-off meeting | 1
2020-09-03 | 2020-09-07 | Project Proposal Ideas | 4
2020-09-10 | 2020-09-11 | Project Proposal Submission | 1
2020-09-07 | 2020-09-10 | Web Layout Design Ideas | 3
2020-09-11 | 2020-09-23 | Relational Database Design Ideas | 12
2020-09-11 | 2020-09-12 | Created Accounts Pages | 1
2020-09-24 | 2020-09-25 | Virtual Presentation | 1
2020-09-25 | 2020-10-01 | Final Database Design | 6
2020-10-01 | 2020-10-07 | Sync Database to website | 6
2020-09-25 | 2020-10-03 | Building HTML / CSS Scripts for Home Page | 8
2020-10-04 | 2020-10-14 | Building HTML / CSS Scripts for Bio and Recipes | 10
2020-10-15 | 2020-10-22 | Final HTML / CSSS / JAVA SCRIPT | 7
2020-10-23 | 2020-11-12 | Product Testing and Evaluation | 19

## Useful Tips
USEFUL TIPS
1 | When enteringactivity start and end dates in columns "C" and "D" use the following date format: DD/MM/YYYY
2 | To change colour of fill and text in cells, use HOME -> FONT tool palette.
3 | To change the start date shown on the gantt chart: Fotmat -> (Current Selection tab) Format Selection -> Axis Options -> Bound: Minimum -> Change value to a number that will be appropriate for your project start date. e.g. 43831 = 1/1/2020 44197 = 1/1/2021 44562 = 1/1/2022 .....

## ©
© TemplateLab.com